## Sheet1
| Feature | Feature Details | Task | Task Details | Owner | Start Date | End Date - Development | Cloud Available Date
1 | UX | css creation | css creation | create css for all forms | Pravin
|  | style creation |  | create css for all controls on form
create css for form header and footer
|  |  | style creation | create styles for all buttons (without click and onclick should cover)
create style for hover on form controls
2 | DICOM Integration with Angular WebApp | DICOM Integration | DICOM Integration |  | Varun
3 | User/Doctor Preference Management
4 | User Managment
5 | Search + Pagination + sorting | search | date wise search | add search fields on all search forms. | Pallavi
|  | pagination | pagination | apply pagination to search
|  | sorting | sorting | on coloumn head click automatically sort the data
6 | Billing Management
7 | Word Document Editor in Webapp | Word Document Editor in Webapp | Word Document Editor in Webapp | create demo for Word Document Editor in Webapp | Varun
8 | Support for Templates |  |  |  | Varun
9 | Block/Unblock Center | Block/Unblock Center | Block/Unblock Center | admin can block and unblock center for some time .add this flag in center database.also add date for how much time center had blocked... | Pallavi | ????can we send notification to centers email address or owner person about block and unblock center | we can send notofication to center email address.
10 | Upload DICOM Images | Upload DICOM Images | Upload DICOM Images | need to discuss with sujit how to upload images on server...becouse there are n number of images per study | Pallavi
11 | DICOM Image Management | DICOM Image Management | DICOM Image Management | need to discuss with sujit | Pallavi
12 | Column Management on Screen using Swipe |  |  |  | Pravin
13 | Infra Readiness |  |  |  | Sujit